## Sheet1
Task Name | Duration | Contributor | Start | Finish | Role
TickTake App | 26 | Everyone | 2023-12-30 | 2024-01-25
Project Management:
Requiments gathering | 2 | Syed Kaif Ali | 2023-12-30 | 2024-01-01 | Project Manager
Project Report | 1 | Syed Kaif Ali | 2024-01-24 | 2024-01-25 | Project Manager
Timeline of the Project | Ongoing | Syed Kaif Ali | 2023-12-30 | 2024-01-01 | Project Manager
Business Analyst:
Work flow of app | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
Competitor Analysis | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
TickTake App Analysis | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
UI Design:
Create UI design on figma | 5 | Taha Mir | 2024-01-01 | 2024-01-06 | UI Designer
DataBase Schema:
Design database schema | 2 | Hamid | 2024-01-01 | 2024-01-03 | Back-end
App UI/Logic implementation:
Event Manager Front-end:
Event Creation | 5 | Mustassum Tanvir | 2024-01-09 | 2024-01-14 | App Front-end
Account creation | 5 | Mustassum Tanvir | 2024-01-09 | 2024-01-14 | App Front-end
Log in | 5 | Mustassum Tanvir | 2024-01-09 | 2024-01-14 | App Front-end
Log out | 5 | Mustassum Tanvir | 2024-01-09 | 2024-01-14 | App Front-end
Approve tickets | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
Cancel tickets | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
Remove events | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
User Front-end:
Open events | 4 | Ahmad Irfan | 2024-01-17 | 2024-01-21 | App Front-end
View upcoming events | 4 | Ahmad Irfan | 2024-01-17 | 2024-01-21 | App Front-end
View past events | 4 | Ahmad Irfan | 2024-01-17 | 2024-01-21 | App Front-end
View favorite events | 5 | Abdul Majid | 2024-01-18 | 2024-01-23 | App Front-end
Remove events from favorites | 5 | Abdul Majid | 2024-01-18 | 2024-01-23 | App Front-end
Buy ticket for an event | 5 | Abdul Majid | 2024-01-18 | 2024-01-23 | App Front-end
Generate QR code | 6 | Ahmad Irfan | 2024-01-19 | 2024-01-25 | App Front-end
Sort events | 6 | Ahmad Irfan | 2024-01-19 | 2024-01-25 | App Front-end
View events by categories | 6 | Ahmad Irfan | 2024-01-19 | 2024-01-25 | App Front-end
Formulas:
Duration = DATEDIF([Start], [Finish], "d")